## RiskCalculationSheet
Probability of Occurrence
Very Unlikely | 1
Somewhat unlikely | 3
50-50 possibility | 5
Somewhat likely | 7
Very likely | 9
Impact of Risk |  | Financial | Operational | Competitive Risks | Reputational | Technical | Legal/Compliance
Very Low | 1 | Maintainance costs | Change Management |  | Efficient and timely immigration processing for enhanced user experience | Algorithm Performance | Vendor compliance
Somewhat Low | 2 | Techn obsolescence | Limited human capital |  | Sytem failure | Malicious/adversary attack tolerance
Moderate | 4 | Vendor Lock-In with increased cost of upgrades or modifications to switch to another tech provider | Third-party tool dependancy for operations and vendor releability | Tech readiness and user experience |  | System scalability | Conflict with regulatory standards of transparency and explainability ffor AI decisions
Somewhat High | 6 | Legal and litigation costs of compliance settlement for possible AI produced legal issues | Integration issues with the existing infrustructure/database leading to disruption in immigration processing | Decision accuracy by rivals (the US, UK, EU, Australia) | minimal human touch in decisions for algorithmic blind spot empathy | Training data quality | Bias and Discrimination legal costs
High | 8 | Cost Savings through tech efficiency | Data accuracy | Cost of lagging in tech adoption | Data privacy breaches | Algorithmic bias | Regulatory Changes that call for adjustments to the exisiting AI systems
Extremely High | 9 | Initial operational costs for human capital and physical capital | System failure/down time | Global market competition from rival agencies using AI leading to industry standards | Ethical concerns of fairness, algorithmic bias and discrimination issues | Limited training data | compliance risk (privacy and security of applicants)

## RiskRegister
Risk # | The Risk of/That | Likelihood Score | Impact Score
1 | Maintainance costs | 9 | 1 |  | Likelyhood/Impact | 1 | 2 | 4 | 6 | 8 | 9
2 | Techn obsolescence | 5 | 2 |  | 1 | 1 |  | 1 |  | 1
3 | Vendor Lock-In with increased cost of upgrades or modifications to switch to another tech provider | 7 | 4 |  | 3 |  |  |  | 2 | 1 | 2
4 | Legal and litigation costs of compliance settlement for possible AI produced legal issues | 9 | 6 |  | 5 | 1 | 2 | 1 | 1 | 2 | 1
5 | Cost Savings through tech efficiency | 9 | 8 |  | 7 | 1 | 1 | 2 | 1 |  | 1
6 | Initial operational costs for human capital and physical capital | 9 | 9 |  | 9 | 2 | 1 | 2 | 1 | 2 | 2
7 | Change Management | 7 | 1
8 | Limited human capital | 5 | 2 |  | Likelyhood/Impact | Low Impact | Moderate Impact | High Impact
9 | Third-party tool dependancy for operations and vendor releability | 9 | 4 | Total risk score | Unlikely | Low Risk (1)
10 | Integration issues with the existing infrustructure/database leading to disruption in immigration processing | 3 | 6 |  | Likely |  | Moderate Risk (13)
11 | Data accuracy | 5 | 8 |  | Highly likely |  |  | High Risk (18)
12 | System failure/down time | 7 | 9
13 | Tech readiness and user experience | 1 | 4
14 | Decision accuracy by rivals (the US, UK, EU, Australia) | 3 | 6
15 | Cost of lagging in tech adoption | 9 | 8
16 | Global market competition from rival agencies using AI leading to industry standards | 3 | 9
17 | Efficient and timely immigration processing for enhanced user experience | 9 | 1
18 | Sytem failure | 7 | 2
19 | minimal human touch in decisions for algorithmic blind spot empathy | 5 | 4
20 | Data privacy breaches | 3 | 8
21 | Ethical concerns of fairness, algorithmic bias and discrimination issues | 5 | 9
22 | Algorithm Performance | 1 | 1
23 | Malicious/adversary attack tolerance | 9 | 2
24 | System scalability | 7 | 4
25 | Training data quality | 5 | 6
26 | Algorithmic bias | 5 | 8
27 | Limited training data | 9 | 9
28 | Vendor compliance | 5 | 1
29 | Conflict with regulatory standards of transparency and explainability ffor AI decisions | 9 | 4
30 | Bias and Discrimination legal costs | 7 | 6
31 | Regulatory Changes that call for adjustments to the exisiting AI systems | 1 | 8
32 | compliance risk (privacy and security of applicants) | 3 | 9

## Heatmap
| High | 9 | Risk 17, 1 | Risk 31 | Risk 29, 9 | Risk 6, 4 | Risk 15, 5, 16 | Risk 27, 6
| Moderate | 7 | Risk 32, 7 | Risk 18 | Risk 3, 24, 7 | Risk 30 |  | Risk 12, 15
IMPACT |  | 5 | Risk 21 | Risk 2, 8 | Risk 19 | Risk 25 | Risk 26, 28, 11 | Risk 28
|  | 3 | Risk 12 |  | Risk 30 | Risk 24, 10, 14 | Risk 20
| Low | 1 | Risk 22, 4 |  | Risk 4,13 | Risk 29, 9 | Risk 23 |  | Response plan- 4 maseares
|  |  | 1 | 2 | 4 | 6 | 8 | 9 | avoidance,
|  |  | Low | Moderate |  |  |  | High | mitigation/reduction,
|  |  |  | LIKELIHOOD |  |  |  |  | transfer,
[9 empty] | acceptance | Risk # | The Risk of/That | Likelihood Score | Impact Score
[10 empty] | 13 | Tech readiness and user experience | 1 | 4
[10 empty] | 22 | Algorithm Performance | 1 | 1
[10 empty] | 31 | Regulatory Changes that call for adjustments to the exisiting AI systems | 1 | 8
[10 empty] | 10 | Integration issues with the existing infrustructure/database leading to disruption in immigration processing | 3 | 6
[10 empty] | 14 | Decision accuracy by rivals (the US, UK, EU, Australia) | 3 | 6
[10 empty] | 16 | Global market competition from rival agencies using AI leading to industry standards | 3 | 9
[10 empty] | 20 | Data privacy breaches | 3 | 8
[10 empty] | 32 | compliance risk (privacy and security of applicants) | 3 | 9
[10 empty] | 2 | Techn obsolescence | 5 | 2
[10 empty] | 8 | Limited human capital | 5 | 2
[10 empty] | 11 | Data accuracy | 5 | 8
[10 empty] | 19 | minimal human touch in decisions for algorithmic blind spot empathy | 5 | 4
[10 empty] | 21 | Ethical concerns of fairness, algorithmic bias and discrimination issues | 5 | 9
[10 empty] | 25 | Training data quality | 5 | 6
[10 empty] | 26 | Algorithmic bias | 5 | 8
[10 empty] | 28 | Vendor compliance | 5 | 1
[10 empty] | 3 | Vendor Lock-In with increased cost of upgrades or modifications to switch to another tech provider | 7 | 4
[10 empty] | 7 | Change Management | 7 | 1
[10 empty] | 12 | System failure/down time | 7 | 9
[10 empty] | 18 | Sytem failure | 7 | 2
[10 empty] | 24 | System scalability | 7 | 4
[10 empty] | 30 | Bias and Discrimination legal costs | 7 | 6
[10 empty] | 1 | Maintainance costs | 9 | 1
[10 empty] | 4 | Legal and litigation costs of compliance settlement for possible AI produced legal issues | 9 | 6
[10 empty] | 5 | Cost Savings through tech efficiency | 9 | 8
[10 empty] | 6 | Initial operational costs for human capital and physical capital | 9 | 9
[10 empty] | 9 | Third-party tool dependancy for operations and vendor releability | 9 | 4
[10 empty] | 15 | Cost of lagging in tech adoption | 9 | 8
[10 empty] | 17 | Efficient and timely immigration processing for enhanced user experience | 9 | 1
[10 empty] | 23 | Malicious/adversary attack tolerance | 9 | 2
[10 empty] | 27 | Limited training data | 9 | 9
[10 empty] | 29 | Conflict with regulatory standards of transparency and explainability ffor AI decisions | 9 | 4